## Executive Summary
Executive Summary — Commercialization Program Status
Work Package | Status | Est. Effort (hrs) | Actual Effort (hrs) | Est. Duration (days) | % Complete (effort-weighted) | Gate / Notes
Phase 0 — R&D Diligence | Done | 40 | 40 | 5 | 100% | Complete before coding WPs
WP0 — Foundations | Done | 59 | 61 | 8.5 | 100% | Merged PRs #1–#2
WP1 — Licensing & Compliance | Done | 68 | 72 | 9 | 100% | Merged PRs #3–#5
WP-DEC — Multi-tenancy Decision | Done | 7 | 7 | 1 | 100% | Model A accepted 2026-07-21
Carry-forward / Tech Debt | Open follow-ups | 32 | 2 | 4 | 6.25% | Not blocking WP2 start
Carry-forward / Legal Follow-through | Open follow-ups | 24 | — | 3 | 0% | Launch gates; not eng blockers for WP2
WP2 — Identity & Entra Auth | In Progress | 156 | — | 19.5 | 0.3846% | CURRENT — kickoff in progress
WP3 — Frontend Map + White-label | Pending | 81 | — | 10.2 | 0% | After WP2 (admin UI optional)
WP4 — Backend/API Documentation | Pending | 49 | — | 6.2 | 0% | Can parallel after WP0; better after WP2
WP5 — External Source Connectors | Pending | 120 | — | 15 | 0% | Hard-blocked on WP2 OAuth users
WP6 — Doc Processing Benchmarks | Pending | 84 | — | 10.5 | 0% | Needs target hardware
WP7 — Cross-platform Packaging | Pending | 90 | — | 11.2 | 0% | After WP2+WP3
WP8 — Onboarding & In-app Help | Pending | 70 | — | 8.8 | 0% | LAST — after final flows
PROGRAM TOTAL |  | 880 | 182 |  | 20.07%
Key metrics
Tasks total | 84
Tasks Done | 30
Tasks In Progress | 1
Tasks Pending | 52
Tasks Blocked | 1
Estimated remaining effort (hrs) | 703.4
Estimated remaining duration (eng-days @6h) | 88.2
Calendar hint (1 eng, critical path WP2→8) | ~10–12 weeks after WP2 start (parallelize WP4/WP6)
PRs merged (commercial fork) | #1–#6
Current package | WP2 — Identity & Microsoft Entra ID (kickoff in progress)
Dependency graph (critical path)
WP0 → WP1 → WP-DEC(Model A) → WP2(Auth) → WP3(White-label) & WP5(Connectors) → WP7(Packaging) → WP8(Onboarding) Parallel after foundations: WP4 (Backend map), WP6 (Benchmarks, needs hardware) Carry-forward tech debt / legal ToS can run alongside WP2+

## WBS Task List
Open Notebook Commercialization — Work Breakdown Structure (WBS) & Task Schedule
Product: DataFabricX commercial fork of lfnovo/open-notebook ¦ Repo: HariHaranDFX/open-notebook ¦ Generated: 2026-07-30 ¦ Baseline: upstream-base @ v1.14.0 ¦ Tenancy: Model A (single-tenant per client) ¦ Effort basis: engineering estimates (hrs); Actuals filled where known from delivered PRs
Status: Done ¦ In Progress ¦ Pending ¦ Blocked ¦ Duration assumes ~6 productive eng hrs/day ¦ Critical path: WP0→WP1→WP-DEC→WP2→(WP3∥WP5)→WP7→WP8; WP4∥WP6 can parallel after foundations
WBS ID | Phase / Work Package | Task Name | Detailed Description / Steps | Deliverable(s) | Status | Priority | Depends On (WBS) | Est. Effort (hrs) | Est. Duration (days) | Actual Effort (hrs) | % Complete | Owner / Role | Target Start | Target Finish | Actual Finish | Acceptance Criteria | Risks / Notes | Evidence / PR / Doc
0.0 | Phase 0 — R&D Diligence | Commercialization R&D dossier | Purpose: establish whether the upstream Open Notebook codebase can be sold commercially without a licence dead-end. Steps: (1) inventory core and dependency licences; (2) assess SurrealDB BSL 1.1 for embedded/commercial use vs migration cost; (3) scan provider terms for commercial restrictions; (4) write the R&D dossier and SurrealDB migration assessment so later WPs have evidence, not guesses. | R&D dossier; SurrealDB migration assessment | Done | High | — | 24 | 3 | 24 | 100% | Engineering Lead | 2026-07-14 | 2026-07-18 | 2026-07-18 | R&D dossier exists and informs the master plan | Pre-coding foundation; not a feature work package | docs/commercialization/*
0.1 | Phase 0 — R&D Diligence | Master implementation plan authored | Purpose: turn R&D conclusions into an executable program. Steps: (1) define WP0–WP8 with objectives, tasks, and acceptance criteria; (2) draw the hard dependency graph (auth before white-label and SharePoint); (3) set execution rules — one branch per WP, tests required, stop for human review; (4) publish the plan under docs/commercialization/. | open-notebook-master-implementation-plan.md | Done | Critical | 0.0 | 16 | 2 | 16 | 100% | Engineering Lead | 2026-07-18 | 2026-07-20 | 2026-07-20 | Plan covers Phases 1–8 mapped to WPs; one-branch-per-WP rules defined | Plan text still cites v1.10.0; fork baseline is v1.14.0 | docs/commercialization/open-notebook-master-implementation-plan.md
1.0 | WP0 — Foundations | WP0 kickoff & branch | Purpose: open the foundations package cleanly so no feature work mixes into the baseline. Steps: (1) create branch wp-0-foundations from main; (2) confirm remotes; (3) read root and directory CLAUDE.md / AGENTS.md before editing. | Branch wp-0-foundations | Done | Critical | 0.1 | 1 | 0.25 | 1 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | Branch exists; no feature work mixed in |  | PR #1
1.1 | WP0 — Foundations | Fork hygiene: remotes + upstream-base tag | Purpose: freeze the exact upstream commit we forked from so future merges and audits have a clear baseline. Steps: (1) confirm origin points at HariHaranDFX/open-notebook; (2) add upstream lfnovo/open-notebook; (3) tag the fork point as upstream-base; (4) document remotes in DEV_SETUP.md. | git tag upstream-base; upstream remote | Done | Critical | 1.0 | 2 | 0.25 | 2 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | upstream-base tag exists; upstream remote configured | Tagged at 30c7e2a / v1.14.0 (not v1.10.0) | tag: upstream-base
1.2 | WP0 — Foundations | Reproduce clean build & document DEV_SETUP | Purpose: prove a new machine can stand up the stack without tribal knowledge. Steps: (1) install backend with uv and start the API; (2) start SurrealDB via compose; (3) start the worker; (4) install/build the frontend; (5) record exact Windows and Linux steps, known failures, and coverage baselines in docs/DEV_SETUP.md. | docs/DEV_SETUP.md | Done | Critical | 1.1 | 8 | 1 | 10 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | Clean build reproducible from DEV_SETUP on a fresh machine | Later note: on Windows use 127.0.0.1 not localhost for SurrealDB | docs/DEV_SETUP.md
1.3 | WP0 — Foundations | Characterization tests — notebook CRUD | Purpose: lock today’s notebook API behaviour so later auth/ownership work cannot silently break CRUD. Steps: write pytest characterization covering create, read, update, and delete of notebooks; treat failures as regressions unless the test is updated deliberately in the same change. | tests/characterization/ (CRUD) | Done | High | 1.2 | 6 | 1 | 6 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | CRUD characterization tests exist and pass | Intentional behaviour changes must update the test in the same commit | tests/characterization/
1.4 | WP0 — Foundations | Characterization tests — source ingestion | Purpose: capture the real ingestion path (upload / URL / text → content-core → jobs) as a regression net. Steps: add characterization coverage for the critical source ingestion flows used in production; note gaps found during testing for later product work (not WP0 scope). | tests/characterization/ (ingestion) | Done | High | 1.2 | 8 | 1 | 8 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | Ingestion characterization tests pass | Product gap noted later: uploaded .html/.json/.png limits | tests/characterization/
1.5 | WP0 — Foundations | Characterization tests — search (text + vector) | Purpose: protect both keyword and vector/semantic search behaviour before commercial features change data access patterns. Steps: add fixed-fixture characterization for text search and vector search endpoints; keep fixtures stable so CI failures mean real drift. | tests/characterization/ (search) | Done | High | 1.2 | 6 | 1 | 6 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | Search characterization tests pass |  | tests/characterization/
1.6 | WP0 — Foundations | Characterization tests — chat | Purpose: baseline the notebook chat / ask critical path so auth and model changes do not break the core product loop. Steps: add characterization for the chat path (provider calls mocked where needed); assert response shape and error handling match current behaviour. | tests/characterization/ (chat) | Done | High | 1.2 | 6 | 1 | 6 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | Chat characterization tests pass |  | tests/characterization/
1.7 | WP0 — Foundations | Coverage ratchet (backend + frontend) | Purpose: stop coverage from silently declining as the commercial fork grows. Steps: enable coverage tooling; record baselines (backend ≥56%, frontend ≥35.79% statements); document that coverage may only increase. | Coverage config + baseline in DEV_SETUP.md | Done | High | 1.3 | 4 | 0.5 | 4 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | Baselines recorded; ratchet documented/enforced |  | docs/DEV_SETUP.md
1.8 | WP0 — Foundations | CI pipeline: lint, typecheck, tests, build | Purpose: make every PR prove the fork still builds and tests before merge. Steps: configure GitHub Actions for Backend Tests / Lint / Typecheck and Frontend Tests / Lint / Build; require green checks before merge to main. | CI workflow green on PR | Done | Critical | 1.7 | 8 | 1 | 8 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | CI runs on PR and blocks merge on failure | Seven required checks including License Scan | PR #1
1.9 | WP0 — Foundations | License scan in CI (GPL/AGPL drift guard) | Purpose: catch copyleft dependencies the moment they appear via a transitive update. Steps: implement scripts/check_licenses.py; wire the License Scan CI job; fail on non-allowlisted GPL; never allowlist AGPL; require a written justification for any allowlist entry. | scripts/check_licenses.py + CI job | Done | Critical | 1.8 | 6 | 1 | 6 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | License scan runs in CI and passes | Allowlist is a reviewed decision list, not a shortcut | scripts/check_licenses.py
1.10 | WP0 — Foundations | Branch protection on main | Purpose: enforce the PR-only workflow even for admins. Steps: require the seven checks; require branch up to date with main; reject direct pushes; disable force-push and branch deletion; verify with a probe push. | Protected main branch | Done | Critical | 1.8 | 2 | 0.25 | 2 | 100% | Maintainer | 2026-07-21 | 2026-07-21 | 2026-07-21 | Direct push rejected; PRs required |  | PR #2
1.11 | WP0 — Foundations | WP0 close-out docs + human review | Purpose: formally close foundations before licensing work starts. Steps: update status docs; merge remaining WP0 PR; confirm all five WP0 acceptance criteria; stop for human review before WP1. | WP0 complete on main; PRs #1–#2 | Done | High | 1.9,1.10 | 2 | 0.25 | 2 | 100% | Engineering Lead | 2026-07-21 | 2026-07-21 | 2026-07-21 | All five WP0 acceptance criteria pass |  | PR #2
2.0 | WP1 — Licensing & Compliance | WP1 kickoff & branch | Purpose: start licensing work on an isolated branch with the company legal name fixed. Steps: create wp-1-* branches as needed; use legal name DataFabricX Pvt Ltd; keep SurrealDB (already decided); exclude unrelated feature work. | Branches wp-1-* | Done | Critical | 1.11 | 1 | 0.25 | 1 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | WP1-only scope |  | PR #4
2.1 | WP1 — Licensing & Compliance | Preserve attribution + add DataFabricX copyright | Purpose: meet MIT attribution while asserting our commercial copyright. Steps: add a DataFabricX copyright block above Luis Novo’s retained MIT copyright in LICENSE; never replace or remove upstream copyright; ship LICENSE with the product. | LICENSE updated | Done | Critical | 2.0 | 2 | 0.25 | 2 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | LICENSE retains upstream copyright + our copyright |  | LICENSE; PR #4
2.2 | WP1 — Licensing & Compliance | Purge asciidoc (GPLv2+) from shipped image | Purpose: avoid distributing GPLv2+ in commercial images even when the library is unmodified. Why it matters: GPL obligations attach on distribution; Docker images are distribution. Unmodified use does not make GPLv2+ safe to ship. Steps: (1) purge asciidoc from the shipped image; (2) keep a reviewed allowlist entry for local/CI only; (3) open upstream content-core#58 to remove the dependency properly; (4) add a guard test; (5) when upstream merges and we bump, drop purge and allowlist together. | Dockerfile purge; content-core#58; tests | Done | Critical | 2.0 | 8 | 1 | 10 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | No asciidoc in shipped image | Follow-up 3.8 removes the temporary purge after upstream bump | PR #3; lfnovo/content-core#58
2.3 | WP1 — Licensing & Compliance | Generate THIRD-PARTY-NOTICES.md (Linux) | Purpose: publish an accurate attribution list for every third-party component we distribute. Steps: auto-generate Python + frontend notices; fix bad/UNKNOWN fields (tiktoken licence text dump, caio/content-core); add SurrealDB BSL entry; require Linux generation; add CI drift detection so the file cannot go stale unnoticed. | THIRD-PARTY-NOTICES.md; scripts/generate_notices.py | Done | Critical | 2.1,2.2 | 12 | 1.5 | 14 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | Notices complete, reproducible, CI-guarded | Must be regenerated on Linux | PR #4
2.4 | WP1 — Licensing & Compliance | pycountry unmodified integrity guard | Purpose: keep LGPL-2.1 obligations at zero by never modifying or vendoring pycountry. Steps: document the rule in LICENSE_COMPLIANCE; add tests/test_pycountry_unmodified.py that hashes installed files against the package RECORD; fail CI if a byte changes. | Integrity test + compliance docs | Done | High | 2.1 | 4 | 0.5 | 4 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | pycountry documented unmodified; CI asserts |  | tests/test_pycountry_unmodified.py
2.5 | WP1 — Licensing & Compliance | SurrealDB BSL: multi-container path documented | Purpose: record why pulling the official SurrealDB image is not redistribution, and why we keep BSL. Steps: document the default compose path (official image as a dependency); record Additional Use Grant position for commercial embedding; cite the pinned SurrealDB version’s terms. | LICENSE_COMPLIANCE.md SurrealDB section | Done | High | 2.3 | 3 | 0.5 | 3 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | BSL entry accurate for pinned SurrealDB version | Business decision: keep SurrealDB (see LEGAL_DECISIONS) | docs/LICENSE_COMPLIANCE.md
2.6 | WP1 — Licensing & Compliance | Ship BSL text inside single-container image | Purpose: when Dockerfile --target single copies the SurrealDB binary into our image, that is redistribution and the BSL text must travel with it. Steps: vendor licenses/SURREALDB-BSL-1.1.txt from the matching SurrealDB tag; COPY into /app/licenses/; verify inside a real built image; re-fetch if the pin changes. | licenses/SURREALDB-BSL-1.1.txt + Dockerfile | Done | Critical | 2.5 | 6 | 1 | 6 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | BSL text present in single image filesystem | Official SurrealDB image ships no licence file of its own | PR #5
2.7 | WP1 — Licensing & Compliance | PROVIDER_TERMS.md for all providers | Purpose: ensure every provider the product can call has a reviewed commercial-terms pointer before sales. Steps: list all enabled providers (~22) with ToS links; flag PRC-jurisdiction providers, ElevenLabs commercial audio rights, and local model-weight licences for follow-through. | docs/PROVIDER_TERMS.md | Done | High | 2.0 | 8 | 1 | 8 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | PROVIDER_TERMS.md exists for all providers | Re-verify links before commercial launch (task 3.11) | docs/PROVIDER_TERMS.md
2.8 | WP1 — Licensing & Compliance | Encryption key handling documentation | Purpose: prevent encryption keys from being committed or shared across deployments. Steps: document OPEN_NOTEBOOK_ENCRYPTION_KEY / _FILE — generate per deployment, never commit, rotation guidance — in LICENSE_COMPLIANCE. | Encryption section in compliance docs | Done | High | 2.0 | 2 | 0.25 | 2 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | No secrets committed; key handling documented |  | docs/LICENSE_COMPLIANCE.md
2.9 | WP1 — Licensing & Compliance | LICENSE_COMPLIANCE.md standing rules | Purpose: give every future dependency change a single binding rulebook. Steps: write standing rules (no GPL/AGPL; no PyMuPDF/poppler; pycountry unmodified; notices regeneration; brand inventory deferred to WP3). | docs/LICENSE_COMPLIANCE.md | Done | High | 2.3,2.7 | 6 | 0.75 | 6 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | Rules readable before any dependency add | Rebranding correctly deferred to WP3 | docs/LICENSE_COMPLIANCE.md
2.10 | WP1 — Licensing & Compliance | Legal decisions record (business accept/assign) | Purpose: record DataFabricX business decisions on each WP1 risk — accept, assign to client, or fix in code — without pretending to be counsel advice. Steps: create LEGAL_DECISIONS.md covering SurrealDB keep, single-image BSL fix, PRC providers, ElevenLabs, local model weights, and customer-configured endpoints; list remaining ToS/product follow-through. | docs/LEGAL_DECISIONS.md | Done | Critical | 2.5,2.7 | 6 | 0.75 | 6 | 100% | Product Owner + Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | Six items decided with conditions; engineering diligence recorded | Customer ToS wording still outstanding (task 3.9) | PR #5; docs/LEGAL_DECISIONS.md
2.11 | WP1 — Licensing & Compliance | Windows test/docs hardening (WP1 follow-up) | Purpose: make local Windows verification trustworthy for the team. Steps: fix make start-all issues; correct path/symlink test failures; document SURREAL_URL using 127.0.0.1 because localhost can hit an IPv6 stall and false “database offline” under a 2s health budget. | DEV_SETUP updates; Windows test fixes | Done | Medium | 2.6 | 8 | 1 | 8 | 100% | Engineer | 2026-07-21 | 2026-07-22 | 2026-07-22 | Documented Windows pitfalls; tests green where applicable | Found during local verification of WP1 | PR #5
2.12 | WP1 — Licensing & Compliance | WP1 merge + close-out | Purpose: land licensing on main and free the critical path for tenancy decision + auth. Steps: merge PRs #3–#5; confirm WP1 acceptance criteria; stop for human review before WP2 feature work. | WP1 on main | Done | Critical | 2.10,2.11 | 2 | 0.25 | 2 | 100% | Engineering Lead | 2026-07-21 | 2026-07-21 | 2026-07-21 | All WP1 acceptance criteria met |  | PRs #3,#4,#5
3.0 | WP-DEC — Multi-tenancy Decision | Choose Model A vs Model B | Purpose: pick the tenancy model before auth/theming/connectors are built (building the wrong model means rebuilding). Model A: one isolated instance per client (physical separation). Model B: one instance, many clients, tenant_id on every row. Decision: Model A for first commercial release — isolation is architectural, matches per-client install/branding, lower eng cost; revisit if ops cost or self-serve free tier forces multi-tenant. | Decision recorded | Done | Critical | 2.12 | 4 | 0.5 | 4 | 100% | Product Owner | 2026-07-21 | 2026-07-21 | 2026-07-21 | ONE model chosen and documented before WP2 | Approved by DataFabricX 2026-07-21 | docs/TENANCY.md
3.1 | WP-DEC — Multi-tenancy Decision | Document TENANCY.md consequences | Purpose: make the Model A choice binding for downstream packages. Steps: document implications for WP2 (user_id + client_id), WP3 (brand at startup), WP5 (per-user tokens), WP7 (installer = one instance); list revisit triggers; note LEGAL_DECISIONS depends on client-operated instances. | docs/TENANCY.md | Done | Critical | 3.0 | 3 | 0.5 | 3 | 100% | Engineer | 2026-07-21 | 2026-07-21 | 2026-07-21 | TENANCY.md accepted; WP2/3/5/7 assume Model A | If DataFabricX hosts instances or supplies provider keys, reopen with LEGAL_DECISIONS | docs/TENANCY.md
3.4 | Carry-forward / Tech Debt | Adopt esperanto 2.26.0 (Azure STT verbose_json fix) | Purpose: pull the upstream fix for Azure gpt-4o-*-transcribe failures caused by hardcoded response_format=verbose_json. Filed as lfnovo/esperanto#263; fixed in esperanto PR #270 and released in v2.26.0. Steps: bump floor to >=2.26.0; refresh lock + notices; keep our PR #6 nested STT config (still required — AzureSpeechToTextModel remains a dataclass that only reads nested config). | App on esperanto >=2.26.0; Azure non-Whisper STT format resolved upstream | Done | High | 2.12 | 2 | 0.25 | 2 | 100% | Engineer | 2026-07-30 | 2026-07-30 | 2026-07-30 | Locked to esperanto 2.26.0; _resolve_transcription_response_format used by Azure STT | No local verbose_json workaround existed; PR #6 nesting kept on purpose | https://github.com/lfnovo/esperanto/issues/263 · v2.26.0
3.5 | Carry-forward / Tech Debt | Azure credential form: api_version field | Purpose: fix a product bug found during WP1 local testing — Azure OpenAI requires an API version, but the credential form has no field for it. Impact: embeddings, transformations, and chat fail when api_version is null even if key and endpoint are set. Steps: add api_version to CredentialFormDialog and persistence; verify connection + real inference; keep separate from WP2 scope. | Working Azure credential UI | Pending | High | 2.12 | 8 | 1 |  | 0% | Engineer | 2026-08-04 | 2026-08-05 |  | User can set api_version in UI; connection + inference succeed | PR #6 nested STT config kept; esperanto#263 transcription format fixed via task 3.4 | Bug found 2026-07-22
3.6 | Carry-forward / Tech Debt | Upstream Azure GA API support in esperanto | Purpose: track the library gap where Azure’s newer GA surface still is not fully usable from this app without an api-version query parameter. Steps: follow esperanto#262; adopt the upstream fix when available or keep documenting the supported preview/api-version pins; do not block WP2 on this. | Upstream fix or documented workaround | Pending | Medium | 3.5 | 4 | 0.5 |  | 0% | Engineer | 2026-08-04 | 2026-08-08 |  | Connection/inference path documented and stable for supported versions | Filed as lfnovo/esperanto#262 — still open (separate from #263 / task 3.4) | https://github.com/lfnovo/esperanto/issues/262
3.7 | Carry-forward / Tech Debt | Upload support for .html / .json / .png | Purpose: close extraction gaps found while testing — uploaded .html is rejected (inline HTML works), and .json/.png need Docling or pipeline work. Steps: decide supported matrix; implement or document clearly; optionally fold into WP5/WP6 rather than a one-off. | Supported upload types documented + implemented as needed | Pending | Medium | 1.4 | 16 | 2 |  | 0% | Engineer | 2026-08-11 | 2026-08-13 |  | Documented types work via the upload path | Product gap, not a licensing issue | Noted in CLAUDE.md
3.8 | Carry-forward / Tech Debt | Drop asciidoc purge after content-core bump | Purpose: remove the temporary Dockerfile purge once upstream stops pulling asciidoc. Blocked on: lfnovo/content-core#58 merge + dependency bump here. Steps: bump content-core; delete purge; remove allowlist entry in the same change; confirm License Scan still green. | Cleaner image; allowlist reduced | Blocked | Low | 2.2 | 2 | 0.25 |  | 0% | Engineer |  |  |  | asciidoc gone from allowlist and Dockerfile | Blocked on upstream PR | content-core#58
3.9 | Carry-forward / Legal Follow-through | Customer ToS wording (model weights & endpoints) | Purpose: make the LEGAL_DECISIONS assignments to the client enforceable in a document the customer actually signs. Why it matters: you decided that local model-weight licences (Ollama/oMLX) and customer-configured OpenAI/Anthropic-compatible endpoints are the client’s responsibility. That assignment only holds if the customer agrees in writing; an internal decision file is not enough. Steps: (1) draft ToS clauses for items 5–6 (and ideally item 3 / PRC providers); (2) legal/product review; (3) include in customer paperwork before commercial launch. Not an engineering blocker for WP2; it is a commercial-launch gate. | Customer ToS draft sections | Pending | High | 2.10,3.1 | 8 | 1 |  | 0% | Legal / Product | 2026-08-04 | 2026-08-08 |  | Customer has written agreement covering the assignments | Blocks launch paperwork, not WP2 coding | docs/LEGAL_DECISIONS.md
3.10 | Carry-forward / Legal Follow-through | PRC providers opt-in (not default) | Purpose: make “client chooses PRC-jurisdiction providers” a real choice, not a silent default. Providers: DeepSeek, DashScope (Qwen), MiniMax. Why it matters: LEGAL_DECISIONS assigns residency risk to the client only if the client enables those providers deliberately. If they are on by default, research content can be routed to a PRC jurisdiction without an explicit decision. Steps: (1) default those providers off per deployment; (2) require explicit enable; (3) UI copy stating data-residency implication at enable time. Track during WP2/WP3 provider-configuration UI work. | Opt-in provider config + UI copy | Pending | High | 2.10 | 12 | 1.5 |  | 0% | Engineer | 2026-08-18 | 2026-08-20 |  | PRC providers off by default; enabling requires explicit choice with residency notice | LEGAL_DECISIONS item 3 outstanding product action | LEGAL_DECISIONS item 3
3.11 | Carry-forward / Legal Follow-through | Re-verify PROVIDER_TERMS links pre-launch | Purpose: ensure every commercial ToS link in PROVIDER_TERMS.md is still live and still matches what we claim before launch. Why it matters: providers change terms and URLs without notice; a stale link is a compliance gap at the moment you sell. Steps: walk every entry; fix dead/moved URLs; note material term changes for product/legal; schedule as a launch checklist item. | Updated PROVIDER_TERMS.md | Pending | Medium | 2.7 | 4 | 0.5 |  | 0% | Legal / Engineer |  |  |  | All links live; terms still accurately summarised | Launch gate; repeatable checklist | docs/PROVIDER_TERMS.md
4.0 | WP2 — Identity & Entra Auth | WP2 kickoff: branch + spike | Purpose: open the identity package and lock Entra prerequisites before coding middleware. Steps: (1) create branch wp-2-entra-auth; (2) spike Entra app registration (redirect URIs, API permissions, admin consent); (3) confirm Model A assumptions from TENANCY.md; (4) re-read WP2 design in the master plan; (5) list env vars and local password-fallback behaviour. This is the program critical-path start: white-label (WP3) and SharePoint connectors (WP5) both need real users/tokens. | Branch + spike notes / Entra checklist | In Progress | Critical | 3.1 | 4 | 0.5 |  | 15% | Engineer | 2026-08-01 | 2026-08-01 |  | Branch ready; Entra app registration checklist drafted | Current work package kickoff | Plan WP2; CLAUDE.md current WP = WP2
4.1 | WP2 — Identity & Entra Auth | Backend AuthProvider abstraction | Purpose: stop hard-wiring password auth so Entra (and later other IdPs) plug in without rewriting every route. Steps: create api/auth/ with an AuthProvider protocol; move existing password logic into PasswordAuthProvider; select provider via config; keep password mode as local-dev fallback. | api/auth/ + PasswordAuthProvider | Pending | Critical | 4.0 | 12 | 1.5 |  | 0% | Backend Engineer | 2026-08-01 | 2026-08-04 |  | Password provider still works as local-dev fallback behind a flag | Preserve existing password behaviour for tests
4.2 | WP2 — Identity & Entra Auth | EntraOIDCProvider — JWT validation | Purpose: validate real Microsoft Entra tokens on the API — issuer, audience, signature (JWKS), expiry, and claims. Steps: implement EntraOIDCProvider; configure ENTRA_TENANT_ID, ENTRA_CLIENT_ID, ENTRA_CLIENT_SECRET, ENTRA_REDIRECT_URI, AUTH_PROVIDER=entra; reject invalid tokens with clear 401s. | EntraOIDCProvider | Pending | Critical | 4.1 | 20 | 2.5 |  | 0% | Backend Engineer | 2026-08-04 | 2026-08-07 |  | API accepts valid Entra JWTs and rejects invalid/expired ones | Use maintained JWT/JWKS libraries
4.3 | WP2 — Identity & Entra Auth | AuthMiddleware + request user context | Purpose: replace the single shared-password middleware with provider-delegating middleware that attaches the resolved user (and client_id) to each request. Steps: swap PasswordAuthMiddleware for AuthMiddleware; populate request context; ensure unauthenticated calls fail closed in entra mode. | AuthMiddleware | Pending | Critical | 4.2 | 12 | 1.5 |  | 0% | Backend Engineer | 2026-08-07 | 2026-08-08 |  | Every protected API request validates a real Entra token when entra mode is on
4.4 | WP2 — Identity & Entra Auth | User model + SurrealDB migration + JIT provision | Purpose: create a real user record on first successful login (no pre-provisioning required). Steps: add user model (id, email, display name, Entra oid/sub, client_id, role); add migration N.surrealql and AsyncMigrationManager entry; create-or-update on login. | user model + migration | Pending | Critical | 4.3 | 16 | 2 |  | 0% | Backend Engineer | 2026-08-08 | 2026-08-11 |  | User record exists after first successful login | Migrations are hard-coded, not auto-discovered
4.5 | WP2 — Identity & Entra Auth | Roles & authorization on sensitive routes | Purpose: stop every logged-in user from changing models, credentials, and rebuild settings. Steps: define at least admin and user roles; enforce 403 on settings, models, credentials, embedding rebuild, and other sensitive routes. | RBAC checks on sensitive routers | Pending | High | 4.4 | 12 | 1.5 |  | 0% | Backend Engineer | 2026-08-11 | 2026-08-12 |  | Unauthorized callers receive 403 on sensitive routes
4.6 | WP2 — Identity & Entra Auth | Data ownership: user_id (+ client_id) on notebooks/sources | Purpose: move from “all data is global to the instance” to per-user ownership while keeping Model A simple. Steps: add user_id and client_id (constant per deployment under Model A, kept for a future Model B); filter create/read paths; update characterization tests deliberately where behaviour changes. Risk: this is the largest WP2 surface area — missing filters leak another user’s notebooks. | Schema + query ownership filters | Pending | Critical | 4.4 | 24 | 3 |  | 0% | Backend Engineer | 2026-08-12 | 2026-08-15 |  | Users only see their own notebooks/sources | Highest-risk WP2 task
4.7 | WP2 — Identity & Entra Auth | Frontend Entra login (OIDC + PKCE) | Purpose: replace the shared-password login UI with Entra Authorization Code + PKCE. Steps: implement redirect/callback in LoginForm/auth-store; prefer httpOnly cookies over localStorage; silent refresh; logout clears Entra session; guard dashboard routes; CSRF protection if cookie-based. | Entra login UX + session handling | Pending | Critical | 4.3 | 24 | 3 |  | 0% | Frontend Engineer | 2026-08-08 | 2026-08-13 |  | Login via a real Entra account works end-to-end
4.8 | WP2 — Identity & Entra Auth | Stub GenericOIDCProvider (pluggability proof) | Purpose: prove a second identity provider can be added without touching route handlers. Steps: add a minimal GenericOIDCProvider stub and a test demonstrating handlers stay provider-agnostic; SAML remains a later optional extension. | GenericOIDCProvider stub + test | Pending | Medium | 4.1,4.3 | 8 | 1 |  | 0% | Backend Engineer | 2026-08-13 | 2026-08-14 |  | Adding a second provider requires no change to route handlers
4.9 | WP2 — Identity & Entra Auth | docs/AUTH.md | Purpose: give operators a complete Entra setup and extension guide. Steps: document app registration, redirect URIs, API permissions, admin consent, env config, password fallback, and how to add another provider. | docs/AUTH.md | Pending | High | 4.7,4.8 | 8 | 1 |  | 0% | Engineer | 2026-08-14 | 2026-08-15 |  | AUTH.md complete for operators
4.10 | WP2 — Identity & Entra Auth | WP2 tests, CI green, human review stop | Purpose: close WP2 only when acceptance criteria and CI are green, then stop for human review (do not start WP3 on the same branch). Steps: unit/integration/E2E for auth; intentional characterization updates; open PR; merge only when all WP2 criteria pass. | Green PR wp-2-entra-auth | Pending | Critical | 4.5,4.6,4.7,4.9 | 16 | 2 |  | 0% | Engineer | 2026-08-15 | 2026-08-18 |  | All WP2 acceptance criteria pass; CI green | Largest single change in the program
5.0 | WP3 — Frontend Map + White-label | WP3 kickoff | Purpose: start white-label work only after identity is on main. Steps: create wp-3-white-label; confirm Model A brand loads once at app startup (not per request). | Branch | Pending | High | 4.10 | 1 | 0.25 |  | 0% | Frontend Engineer | 2026-08-19 | 2026-08-19 |  | Branch created after WP2 merge | Optional admin brand UI needs WP2 roles
5.1 | WP3 — Frontend Map + White-label | Produce docs/FRONTEND_MAP.md | Purpose: make every future UI change locatable without archaeology. Steps: for each auth and dashboard route, document page → component tree, stores/hooks/API calls, shared layout, component catalog, and a where-do-I-change-X table. | docs/FRONTEND_MAP.md | Pending | High | 5.0 | 20 | 2.5 |  | 0% | Frontend Engineer | 2026-08-19 | 2026-08-21 |  | Map covers every route with data flow + backend calls
5.2 | WP3 — Frontend Map + White-label | BrandConfig schema + loader | Purpose: drive app name, logos, favicon, colours, font, and support URL from config so clients do not need a rebuild. Steps: define BrandConfig schema; load from BRAND_CONFIG_PATH or /config/brand at startup under Model A. | BrandConfig type + loader | Pending | Critical | 5.0 | 12 | 1.5 |  | 0% | Full-stack | 2026-08-21 | 2026-08-22 |  | Config loads without a rebuild
5.3 | WP3 — Frontend Map + White-label | Runtime theme injection (CSS variables) | Purpose: apply BrandConfig at runtime to CSS variables for light and dark themes. Steps: map colours to :root / dark variants; replace hardcoded title and /logo.svg; use the brand inventory in LICENSE_COMPLIANCE §8; demonstrate two brands from one build. | Runtime theming | Pending | Critical | 5.2 | 16 | 2 |  | 0% | Frontend Engineer | 2026-08-22 | 2026-08-25 |  | Two visibly different brands from the same build; no code edit to rebrand
5.4 | WP3 — Frontend Map + White-label | themes/ presets + add-client procedure | Purpose: make “add a client theme” a documented drop-in of config + assets. Steps: ship at least two presets under themes/; write the operator procedure (no rebuild). | themes/ + docs procedure | Pending | High | 5.3 | 8 | 1 |  | 0% | Frontend Engineer | 2026-08-25 | 2026-08-26 |  | Documented procedure produces two different brands from one build
5.5 | WP3 — Frontend Map + White-label | Optional admin BrandConfig UI | Purpose (optional): let admins edit BrandConfig live without redeploying. Steps: admin-only settings screen gated by WP2 roles; persist and hot-apply theme. | Admin brand settings UI | Pending | Low | 5.3,4.5 | 16 | 2 |  | 0% | Frontend Engineer | 2026-08-26 | 2026-08-28 |  | Admin can edit brand without redeploy (optional acceptance) | Optional per master plan
5.6 | WP3 — Frontend Map + White-label | WP3 verification + review stop | Purpose: close white-label only when map + config branding acceptance criteria pass. Steps: verify ACs; PR; human review; do not mix WP5 on the same branch. | Merged WP3 | Pending | High | 5.1,5.4 | 8 | 1 |  | 0% | Engineering Lead | 2026-08-28 | 2026-08-29 |  | All WP3 acceptance criteria pass
6.0 | WP4 — Backend/API Documentation | WP4 kickoff (can parallel early) | Purpose: start the backend architecture map as documentation-only, low-risk work. Steps: create wp-4-backend-map; prefer starting after WP2 so auth docs match reality; can begin after WP0 if staffed in parallel. | Branch | Pending | Medium | 1.11 | 1 | 0.25 |  | 0% | Backend Engineer | 2026-08-19 | 2026-08-19 |  | Docs branch ready | Better after WP2 for accurate auth sections
6.1 | WP4 — Backend/API Documentation | Router catalog (all endpoints) | Purpose: catalogue every HTTP endpoint with method, path, models, auth requirement, and service/domain call. Steps: walk all routers; document consistently; update after WP2 auth lands. | BACKEND_MAP.md routers section | Pending | Medium | 6.0 | 16 | 2 |  | 0% | Backend Engineer | 2026-08-19 | 2026-08-21 |  | Every endpoint documented with auth + models
6.2 | WP4 — Backend/API Documentation | Domain model + graph + data layer maps | Purpose: document ObjectModel patterns, LangGraph flows, repository usage, migrations, and SurrealDB features in use. Steps: catalogue models/relationships; map each graph’s inputs/steps/outputs; explain repository call-site pattern and migrations. | BACKEND_MAP.md domain/graphs/data | Pending | Medium | 6.1 | 16 | 2 |  | 0% | Backend Engineer | 2026-08-21 | 2026-08-25 |  | Every domain model and graph documented
6.3 | WP4 — Backend/API Documentation | Jobs, config/secrets, how-to playbooks | Purpose: finish the operator/engineer map with jobs, env vars, and five how-to-add playbooks. Steps: document surreal-commands; env/secrets; playbooks for endpoint, model+migration, provider, job, source type; reconcile with existing change-playbooks.md. | BACKEND_MAP.md complete | Pending | Medium | 6.2 | 12 | 1.5 |  | 0% | Backend Engineer | 2026-08-25 | 2026-08-26 |  | Five how-to playbooks present and accurate
6.4 | WP4 — Backend/API Documentation | WP4 review stop | Purpose: peer-review the map for accuracy and merge. Steps: review against live code; fix gaps; merge; confirm a new engineer can locate changes using only BACKEND_MAP. | docs/BACKEND_MAP.md on main | Pending | Medium | 6.3 | 4 | 0.5 |  | 0% | Engineering Lead | 2026-08-26 | 2026-08-27 |  | New engineer can locate changes using only this doc
7.0 | WP5 — External Source Connectors | WP5 kickoff | Purpose: design connectors that feed the existing ingestion pipeline instead of reinventing extraction. Steps: create wp-5-connectors; draft SourceConnector interface; confirm hard dependency on WP2 for per-user OAuth tokens. | Branch + design note | Pending | High | 4.10 | 4 | 0.5 |  | 0% | Engineer | 2026-09-01 | 2026-09-01 |  | Design reuses content-core + graphs/source.py | Blocked until WP2 users/tokens exist
7.1 | WP5 — External Source Connectors | SourceConnector interface + bulk job fan-out | Purpose: one “add location” action becomes N document jobs with per-doc progress and partial failure tolerance. Steps: define authenticate/list_documents/fetch_document; extend source_commands for fan-out; ensure one bad file does not abort the batch. | Connector API + bulk command | Pending | Critical | 7.0 | 24 | 3 |  | 0% | Backend Engineer | 2026-09-01 | 2026-09-04 |  | Single failure does not abort batch; progress per document
7.2 | WP5 — External Source Connectors | SharePoint connector (Microsoft Graph) | Purpose: let an Entra-signed-in user pull an entire SharePoint folder into chat-able sources. Steps: OAuth on behalf of the user; least-privilege Sites/Files read scopes; enumerate folder; download supported files into existing ingestion; document admin consent. | SharePointConnector | Pending | Critical | 7.1,4.7 | 32 | 4 |  | 0% | Backend Engineer | 2026-09-04 | 2026-09-10 |  | User connects SharePoint, picks folder, pulls all supported docs
7.3 | WP5 — External Source Connectors | Generic DMS / multi-doc link connector | Purpose: support folder URLs / IDs that resolve to many documents, with an extension point for other DMS systems. Steps: implement base multi-doc connector; keep the SourceConnector interface as the only required surface for new connectors. | Generic multi-doc connector | Pending | High | 7.1 | 16 | 2 |  | 0% | Backend Engineer | 2026-09-08 | 2026-09-10 |  | New connector = implement interface only
7.4 | WP5 — External Source Connectors | Encrypted per-user token storage | Purpose: store connector OAuth tokens encrypted per user using existing encryption-key infrastructure. Steps: persist tokens encrypted; never share across users; respect source-system permissions (never fetch what the user cannot access). | Encrypted token store | Pending | Critical | 7.2,2.8 | 12 | 1.5 |  | 0% | Backend Engineer | 2026-09-10 | 2026-09-11 |  | Tokens encrypted per user; no cross-user leak
7.5 | WP5 — External Source Connectors | Frontend: Add from SharePoint / Link flow | Purpose: ship the operator UX for connect → folder pick → select → progress, then chat across the pulled set. Steps: add sources steps UI; show per-doc progress; ensure i18n for all locales; group pulled docs for chat/search. | Sources UI flow | Pending | High | 7.2,7.3 | 24 | 3 |  | 0% | Frontend Engineer | 2026-09-11 | 2026-09-16 |  | User can chat across the whole pulled set | i18n required for all locales
7.6 | WP5 — External Source Connectors | docs/CONNECTORS.md + WP5 review | Purpose: document Entra scopes/consent and how to add a connector; close WP5 on acceptance criteria. Steps: write CONNECTORS.md; verify ACs; PR; human review stop. | docs/CONNECTORS.md; merged WP5 | Pending | High | 7.4,7.5 | 8 | 1 |  | 0% | Engineer | 2026-09-16 | 2026-09-17 |  | All WP5 acceptance criteria pass
8.0 | WP6 — Doc Processing Benchmarks | WP6 kickoff + enumerate supported types | Purpose: list what content-core actually supports today and what needs work (OCR, EPUB, upload HTML, etc.). Steps: inventory from real code/config; note gaps; create wp-6-benchmarks. Can run after WP0; needs target hardware for later measurement tasks. | Type inventory | Pending | Medium | 1.11 | 8 | 1 |  | 0% | Engineer | 2026-09-01 | 2026-09-02 |  | Supported types documented from real code | No guessed client-facing numbers
8.1 | WP6 — Doc Processing Benchmarks | Build /benchmarks/ harness | Purpose: produce repeatable measured metrics — not estimates — for ingestion, extraction, embedding, memory, and search/chat latency. Steps: build parameterized harness under /benchmarks/; output machine-readable reports. | /benchmarks/ harness | Pending | High | 8.0 | 24 | 3 |  | 0% | Engineer | 2026-09-02 | 2026-09-05 |  | Harness runs repeatably and outputs a metrics report
8.2 | WP6 — Doc Processing Benchmarks | Assemble representative corpus | Purpose: find empirical slowdown/failure points across sizes and types. Steps: assemble small/medium/large/very-large docs plus scanned PDF, audio, and web page; ensure corpus licensing is clean for redistribution in-repo if needed. | Fixed corpus under benchmarks/ | Pending | High | 8.1 | 12 | 1.5 |  | 0% | Engineer | 2026-09-05 | 2026-09-08 |  | Corpus covers the size/type matrix
8.3 | WP6 — Doc Processing Benchmarks | Define accuracy methodology | Purpose: define how accuracy is measured so client claims are defensible. Steps: specify extraction fidelity, retrieval relevance (labeled Q&A), and chat groundedness methods; report per model tier. | Accuracy method doc section | Pending | High | 8.1 | 8 | 1 |  | 0% | Engineer | 2026-09-05 | 2026-09-08 |  | Accuracy reported as method + numbers
8.4 | WP6 — Doc Processing Benchmarks | Run ≥2 hardware profiles | Purpose: gather real numbers on bare-minimum and recommended hardware. Steps: run harness on both profiles; record figures; note local-model vs API-provider resource differences. Requires access to target hardware. | Raw results JSON/CSV | Pending | Critical | 8.2,8.3 | 24 | 3 |  | 0% | Engineer | 2026-09-08 | 2026-09-11 |  | Real measured numbers for both profiles | Hardware access is a dependency
8.5 | WP6 — Doc Processing Benchmarks | docs/PERFORMANCE_AND_SIZING.md + review | Purpose: publish client-facing sizing guidance backed only by harness output. Steps: write types, limits, times, accuracy, min vs recommended hardware; peer review; merge. | docs/PERFORMANCE_AND_SIZING.md | Pending | High | 8.4 | 8 | 1 |  | 0% | Engineer | 2026-09-11 | 2026-09-12 |  | Doc contains measured numbers only
9.0 | WP7 — Cross-platform Packaging | WP7 kickoff | Purpose: package the real authenticated + branded app, not the pre-WP2 password prototype. Steps: create wp-7-packaging only after WP2 and WP3 are on main. | Branch | Pending | High | 5.6,4.10 | 2 | 0.25 |  | 0% | Engineer | 2026-09-18 | 2026-09-18 |  | Starts only after branded + authenticated app exists
9.1 | WP7 — Cross-platform Packaging | Verify Docker Compose on Windows + Linux | Purpose: make containers the recommended identical path on both OSes. Steps: verify docker-compose and Dockerfile.single on Docker Desktop/WSL2 and Linux; document as primary deploy path. | Verified container deploy | Pending | Critical | 9.0 | 16 | 2 |  | 0% | DevOps / Engineer | 2026-09-18 | 2026-09-22 |  | Container deployment verified on both OSes
9.2 | WP7 — Cross-platform Packaging | Native Linux install path (systemd) | Purpose: support customers who refuse containers. Steps: systemd units + install script; document dependencies for common distros; verify on at least one distro. | Linux native docs + scripts | Pending | Medium | 9.1 | 16 | 2 |  | 0% | DevOps / Engineer | 2026-09-22 | 2026-09-24 |  | Verified on ≥1 Linux distro
9.3 | WP7 — Cross-platform Packaging | Native Windows Service path | Purpose: support Windows Server native installs. Steps: Windows Service wrapper; SurrealDB-on-Windows notes; frontend serve docs; verify on Windows Server or equivalent. | Windows native docs + scripts | Pending | Medium | 9.1 | 16 | 2 |  | 0% | DevOps / Engineer | 2026-09-22 | 2026-09-24 |  | Verified on Windows Server or equivalent
9.4 | WP7 — Cross-platform Packaging | Installer helper CLI (interactive + non-interactive) | Purpose: let a non-expert stand up a branded client instance without hand-editing half a dozen files. Steps: CLI for prereq check → collect brand/Entra/provider/DB/encryption → write config → migrate → start → health check; add scripted/non-interactive mode for repeatable installs. | onboard/install CLI | Pending | Critical | 9.1,5.4 | 32 | 4 |  | 0% | Backend Engineer | 2026-09-24 | 2026-09-30 |  | Full install in both modes; scripted branded client stand-up works | Deployment counterpart to WP3 theming
9.5 | WP7 — Cross-platform Packaging | docs/DEPLOYMENT.md + WP7 review | Purpose: one operator guide for container + native + CLI paths. Steps: write DEPLOYMENT.md; verify WP7 ACs; PR; human review. | docs/DEPLOYMENT.md | Pending | High | 9.2,9.3,9.4 | 8 | 1 |  | 0% | Engineer | 2026-09-30 | 2026-10-01 |  | All WP7 acceptance criteria pass
10.0 | WP8 — Onboarding & In-app Help | WP8 kickoff (LAST) | Purpose: build onboarding against final flows only — wizard/tour copy must match the shipped product. Steps: create wp-8-onboarding after WP2/3/5/7 are stable on main. | Branch | Pending | Medium | 9.5,7.6,5.6 | 2 | 0.25 |  | 0% | Frontend Engineer | 2026-10-02 | 2026-10-02 |  | Built against final UX | Must be last in the program sequence
10.1 | WP8 — Onboarding & In-app Help | First-run / admin setup wizard | Purpose: take a fresh instance to a working configured app without tribal knowledge. Steps: detect fresh instance; guide providers/keys, models, brand (admin), connect a source, create first notebook; all copy via i18n. | Setup wizard | Pending | High | 10.0 | 24 | 3 |  | 0% | Frontend Engineer | 2026-10-02 | 2026-10-07 |  | Completing the wizard leaves a working configured app
10.2 | WP8 — Onboarding & In-app Help | User guided tour (core loop) | Purpose: teach the core loop — add source → search → chat → transform → podcast — with an accessible spotlight tour. Steps: implement dismissible/resumable tour; keep steps short; i18n all locales. | Guided tour | Pending | High | 10.1 | 16 | 2 |  | 0% | Frontend Engineer | 2026-10-07 | 2026-10-09 |  | New user can complete the core-loop tour
10.3 | WP8 — Onboarding & In-app Help | Contextual tooltips + empty states + help surface | Purpose: remove dead-ends for new users on every main screen. Steps: tooltips on non-obvious controls; useful empty states; persistent help (docs, shortcuts, restart tour, BrandConfig support URL); all strings in i18n. | Tooltips/empty states/help | Pending | Medium | 10.2 | 20 | 2.5 |  | 0% | Frontend Engineer | 2026-10-09 | 2026-10-14 |  | All copy in i18n; help reachable everywhere | Locale parity required across all locales
10.4 | WP8 — Onboarding & In-app Help | docs/ONBOARDING.md + program close review | Purpose: document onboarding structure and verify program-level definition of done. Steps: write ONBOARDING.md; confirm a new client can be stood up by config + installer only (branded, Entra-auth’d, connectors, Windows/Linux) without per-client code rebuilds. | docs/ONBOARDING.md; program DoD check | Pending | Medium | 10.3 | 8 | 1 |  | 0% | Engineering Lead | 2026-10-14 | 2026-10-15 |  | All WP8 ACs + program definition of done satisfied

## Acceptance Criteria
Work Package Acceptance Criteria Tracker
WP | Criterion | Status | Evidence | Notes
WP0 | Clean build reproducible from docs/DEV_SETUP.md | Done | docs/DEV_SETUP.md
WP0 | upstream-base tag exists; upstream remote configured | Done | git tag upstream-base | v1.14.0 / 30c7e2a
WP0 | Characterization tests: ingestion, search, chat, notebook CRUD | Done | tests/characterization/
WP0 | CI runs on PR and blocks merge on failure | Done | 7 required checks
WP0 | License scan runs in CI and passes | Done | scripts/check_licenses.py
WP1 | LICENSE retains upstream copyright + our copyright | Done | LICENSE | DataFabricX Pvt Ltd
WP1 | THIRD-PARTY-NOTICES.md complete and reproducible | Done | THIRD-PARTY-NOTICES.md | Linux generate only
WP1 | SurrealDB BSL entry present and accurate | Done | Notices + single image licenses/
WP1 | pycountry unmodified; CI asserts | Done | tests/test_pycountry_unmodified.py
WP1 | docs/PROVIDER_TERMS.md exists | Done | docs/PROVIDER_TERMS.md | 22 providers
WP1 | No secrets committed; encryption key handling documented | Done | LICENSE_COMPLIANCE.md
WP-DEC | Tenancy model chosen and documented | Done | docs/TENANCY.md | Model A
WP2 | Login via real Entra account E2E | Pending |  | In progress package
WP2 | Every API request validates Entra JWT (iss/aud/sig/exp) | Pending
WP2 | Users JIT-provisioned; user record after first login | Pending
WP2 | Roles enforced on sensitive routes (403) | Pending
WP2 | Users only see own notebooks/sources | Pending
WP2 | Password provider still works as local-dev fallback | Pending
WP2 | Second provider needs no route-handler changes (stub) | Pending
WP2 | docs/AUTH.md complete | Pending
WP3 | FRONTEND_MAP.md complete with where-to-change table | Pending
WP3 | New client branded by config only (two brands, same build) | Pending
WP3 | Hardcoded brand strings/assets read from BrandConfig | Pending
WP3 | Dark/light both themed correctly | Pending
WP4 | Every router/endpoint documented with auth + models | Pending
WP4 | Every domain model and graph documented | Pending
WP4 | Five how-to-add-X playbooks present | Pending
WP4 | New engineer can locate changes using only BACKEND_MAP | Pending
WP5 | SharePoint connect → folder → pull all supported docs | Pending
WP5 | Ingestion reuses existing pipeline | Pending
WP5 | Batch per-doc progress; single failure non-fatal | Pending
WP5 | Chat across whole pulled set | Pending
WP5 | Tokens encrypted per user; source permissions respected | Pending
WP5 | New connector = SourceConnector interface only | Pending
WP5 | docs/CONNECTORS.md complete | Pending
WP6 | Benchmark harness repeatable with metrics report | Pending
WP6 | PERFORMANCE_AND_SIZING.md has measured numbers (2 profiles) | Pending
WP6 | Supported types + tested size limits + failure points | Pending
WP6 | Accuracy methodology + results per model tier | Pending
WP6 | Min vs recommended hardware justified by numbers | Pending
WP7 | Container deploy verified Windows + Linux | Pending
WP7 | Native install documented/verified Linux + Windows | Pending
WP7 | Installer CLI full install interactive + non-interactive | Pending
WP7 | Scripted install stands up branded client E2E | Pending
WP7 | docs/DEPLOYMENT.md complete | Pending
WP8 | Fresh instance launches setup wizard → working app | Pending
WP8 | Guided tour of core loop completable | Pending
WP8 | Contextual tooltips; all copy in i18n | Pending
WP8 | Every main screen useful empty state | Pending
WP8 | Tour dismissible/resumable; help surface everywhere | Pending
WP8 | docs/ONBOARDING.md complete | Pending
Program | New client by config + installer only (no per-client rebuild) | Pending |  | Definition of Done
Program | Licensing compliant and drift-guarded | Done | WP1 + CI License Scan
Program | Real performance/sizing numbers for clients | Pending | WP6
Program | Backend + frontend fully mapped | Pending | WP3a + WP4

## Estimating Assumptions
Estimating Assumptions & How to Use This Workbook
Topic | Detail
Effort unit | Hours of experienced engineer time (design + implement + test + docs + PR).
Duration | Working days assuming ~6 productive hours/day (meetings/review buffer already outside).
Team model | Default schedule assumes 1 full-time engineer; calendar time shrinks with parallel WPs (WP4/WP6 vs WP2).
Actuals | Actual Effort is filled for completed work from delivered PRs and recorded close-out dates.
Contingency | No pad in task estimates. Recommend +20% management reserve on remaining program for WP2 auth/ownership surprises.
Critical path driver | WP2 (auth + data ownership) — largest single risk and gate for WP3/WP5.
What Done means | Acceptance criteria pass AND tests green AND PR merged to protected main AND human review stop completed.
Not in estimates | Formal counsel fees; Entra tenant procurement; client UAT; sales/marketing; paid hardware for WP6 if unavailable.
Currency of plan | Synced from the master implementation plan, LEGAL_DECISIONS/TENANCY docs, and git main as of 2026-07-30.
Update cadence | Update Status / Actual Effort / % Complete at end of each WP; never mix WPs on one branch.
Sheet guide | Executive Summary = leadership; WBS Task List = full schedule; Acceptance Criteria = DoD checklist; this sheet = estimating rules.
Regenerate | uv run python scripts/generate_wbs_excel.py (task data lives in scripts/wbs_tasks.py).